## Implementation Checklist
# | Task | Phase | Timeline | Status | Owner
1 | Clone OpenClaw repository | Phase 1 | Day 1 | Pending
2 | Install Python dependencies | Phase 1 | Day 1 | Pending
3 | Install Ollama and pull Llama 3.1 70B | Phase 1 | Day 1-2 | Pending
4 | Configure Telegram/WhatsApp integration | Phase 1 | Day 2 | Pending
5 | Test single agent with CLI command | Phase 1 | Day 2 | Pending
6 | Implement fleetos/core/planner.py | Phase 2 | Day 3-4 | Pending
7 | Implement fleetos/core/orchestrator.py | Phase 2 | Day 4-5 | Pending
8 | Build LangGraph state graph | Phase 2 | Day 5 | Pending
9 | Test: 4 parallel agents spawn and complete | Phase 2 | Day 5 | Pending
10 | Implement fleetos/core/memory.py | Phase 3 | Day 6-7 | Pending
11 | Set up Chroma vector store | Phase 3 | Day 6 | Pending
12 | Integrate GraphRAG for knowledge graph | Phase 3 | Day 7 | Pending
13 | Implement auto-skill generation feedback loop | Phase 3 | Day 8 | Pending
14 | Test: Agents share context and improve | Phase 3 | Day 8 | Pending
15 | Implement fleetos/dashboard/app.py | Phase 4 | Day 9-10 | Pending
16 | Display live agent status and metrics | Phase 4 | Day 10 | Pending
17 | Add "Spin New Fleet" button | Phase 4 | Day 11 | Pending
18 | Test: Dashboard reflects real-time activity | Phase 4 | Day 11 | Pending
19 | Implement fleetos/core/verifier.py | Phase 5 | Day 12-13 | Pending
20 | Add confidence scoring to LangGraph | Phase 5 | Day 13 | Pending
21 | Implement Telegram approval flow | Phase 5 | Day 14 | Pending
22 | Test: Low-confidence actions require approval | Phase 5 | Day 14 | Pending
23 | Define template schema | Phase 6 | Day 15 | Pending
24 | Create newsletter_v1.json template | Phase 6 | Day 16-17 | Pending
25 | Create leadgen_agency_v1.json template | Phase 6 | Day 17-18 | Pending
26 | Implement template matcher logic | Phase 6 | Day 19 | Pending
27 | Test: Single command loads full business setup | Phase 6 | Day 20 | Pending
28 | Create k8s/ CRDs for kagent | Phase 7 | Day 21-23 | Pending
29 | Build docker-compose.yml for local testing | Phase 7 | Day 24-25 | Pending
30 | Deploy to Oracle Always Free | Phase 7 | Day 26-28 | Pending
31 | Test: Fleet scales with zero code changes | Phase 7 | Day 29-30 | Pending
32 | Implement self-evolution loop | Phase 8 | Day 31-35 | Pending
33 | Polish CLI and dashboard UX | Phase 8 | Day 36-40 | Pending
34 | Create landing page | Phase 8 | Day 41-43 | Pending
35 | Launch open-source on GitHub | Phase 8 | Day 44-45 | Pending

## Summary
Phase | Timeline | Key Deliverable
Phase 1: Local Setup | Days 1-2 | OpenClaw + Ollama working locally
Phase 2: Basic Orchestration | Days 3-5 | 4 parallel agents, LangGraph DAG
Phase 3: Memory & Evolution | Days 6-8 | Persistent knowledge + auto-skill generation
Phase 4: Dashboard | Days 9-11 | Streamlit command center
Phase 5: Verification | Days 12-14 | VerdictNet critic + human approval
Phase 6: Business Templates | Days 15-20 | Newsletter, Lead-Gen, Micro-SaaS templates
Phase 7: Cloud Scaling | Days 21-30 | Kubernetes + Oracle Always Free
Phase 8: Launch | Days 31-45 | Open-source release + landing page

## Success Metrics
Phase Milestone | Success Criteria | Status
Phase 2 MVP | 4 agents spawn, complete tasks, artifacts aggregated | Pending
Phase 6 MVP | Newsletter template fully operational | Pending
Phase 7 Production | Fleet runs on free tier, scales to cloud | Pending
Phase 8 Launch | 1000+ GitHub stars, 100+ waitlist | Pending